Overall status of the VTS Committee 2014-2018 Work Programme after VTS41:

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Task** | **Start Session** | | **Planned End Session** | | **Revised End Session** | | **Progress Indicator** | | | | | | **Status Overview** | | |
| **Green** | | **Yellow** | | **Red** | |  | | |
| **TD#1 – Operations** | |  | |  | |  | |  | |  | |  | |  |
| 1.1.1. Produce a Guideline on the use of decision support tools in VTS | | 38 | | 39 | | 38 | |  | |  | |  | | **Completed**  **Approved at C59** |
| 1.1.2. Update the VTS Manual | | 38 | | 41 | |  | |  | |  | |  | | **Completed VTS41** |
| 1.1.3. Produce a Guideline on marine casualty incident reporting and recording, including near miss situations as it relates to VTS | | 38 | | 42 | |  | |  | |  | |  | | Commenced VTS38 |
| 1.1.4. Produce a Guideline on Maritime Service Portfolios for VTS | | 40 | | 44 | |  | |  | |  | |  | | Commenced VTS40 |
| 1.1.5. Produce a Guideline on Preparing for IMO Member State Audit Scheme (IMSAS) as it relates to VTS | | 38 | | 40 | |  | |  | |  | |  | | **Completed**  **Approved at C61** |
| 1.1.6. Produce a Guideline on Measures to Evaluate the Effectiveness of a VTS | | 42 | | 44 | |  | |  | |  | |  | |  |
| 1.2.1. Produce a Guideline on public and media relations in special / defined circumstances | | 42 | | 44 | |  | |  | |  | |  | |  |
| 1.3.1. Produce a Recommendation / Guideline on VTS Communications | | 39 | | 44 | |  | |  | |  | |  | | Commenced VTS39 |
| 1.4.1. Develop an “IALA VTS Strategy Paper” with regards to the delivery of VTS in a rapidly changing world and the possible implications for IMO Resolution A.857(20) Guidelines for Vessel Traffic Services | | 38 | | 40 | | 39 | |  | |  | |  | | **Completed**  **Approved at C60** |
| 1.4.2. Review/update/provide input to IMO on Resolution A.857(20) Guidelines for VTS | | 41 | | 44 | |  | |  | |  | |  | |  |
| 1.4.3. Develop and conduct a global VTS Questionnaire | | 38 | | 41 | |  | |  | |  | |  | | To be loaded to IALA web site by 31-03-16 |
| 1.4.4. Produce a Guideline on preparing for Zero Accident Campaign | | 38 | |  | |  | |  | |  | |  | | On hold pending IMO response |
| **TD#2 – Technology** | |  | |  | |  | |  | |  | |  | |  |
| 2.1.1. Produce a Recommendation on the portrayal of VTS information and data | | 41 | | 44 | |  | |  | |  | |  | |  |
| 2.2.1. Develop Guidance on the technical acceptance of a VTS system | | 39 | | 44 | |  | |  | |  | |  | | Commenced VTS39 |
| 2.2.2. Review V-128 – Operational and Technical Performance Requirements for VTS Equipment: | | 38 | | 44 | | 39 | |  | |  | |  | | **Completed**  **Approved at C60** |
| 2.3.1. Provide a Guideline on the technical interface between VTS systems and the systems of other stakeholders | | 41 | | 44 | |  | |  | |  | |  | |  |
| **TD#3 –Training** | |  | |  | |  | |  | |  | |  | |  |
| 3.1.1. Develop a Model Course on Revalidation Process for VTS Qualification and Certification | | 38 | | 41 | |  | |  | |  | |  | | **Completed VTS41** |
| 3.1.2. Produce a VTS Training Manual to complement the V-103 and its model courses | | 40 | | 44 | |  | |  | |  | |  | | commenced VTS40 |
| 3.1.3 Review and update V-103 on the Standards for Training and Certification of VTS Personnel and other IALA guidance to reflect the introduction of V-103/5 | | 42 | | 44 | |  | |  | |  | |  | |  |
| 3.3.1. Develop guidance on human factors and ergonomics in VTS | | 38 | | 43 | |  | |  | |  | |  | | Commenced VTS38 |
| 3.4.1. Develop a Guideline on VTS Awareness for Navigating Officers | | 42 | | 44 | |  | |  | |  | |  | |  |