| Rev.21/11-2011 Preliminary schedule 2011/2012 for the IMO e-navigation |  |  |
| --- | --- | --- |
| WHAT? | WHO? | DEADLINE |
| Submit report to COMSAR 16 | Coordinator | 30.11 |
| Draft report STW 43 | Coordinator | 20.12 |
| Comments on STW report | CG | 21.1 |
| Draft report NAV 58 | Coordinator | Ultimo January(t.b.c.) |
| Submit report to STW 43 | Coordinator | 27.1 |
| Comments on NAV report | CG | March(t.b.c.) |
| Submit report to NAV 58 | Coordinator | Ultimo April(t.b.c.) |
| COMSAR 16 |  | 12-16.03 |
| STW 43 |  | 30.04-04.05 |
| NAV 58 |  | 02-06.07 |